## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a founder, I want to enter a product idea, description, target audience and research objective so that the platform has complete research inputs. | MUST HAVE | None | Purnima | Done
Sprint 1 | Sprint 1 | US-02 | As a founder, I want the system to validate the research input so that incomplete or invalid requests are handled safely. | MUST HAVE | US-01 | Purnima | Done
Sprint 1 | Sprint 1 | US-03 | As a founder, I want AI-generated synthetic personas so that I can represent different potential customers without recruiting real users. | MUST HAVE | US-02 | Purnima | Done
Sprint 1 | Sprint 1 | US-04 | As a researcher, I want each persona to contain demographic and behavioural attributes so that the customer profile is useful for research. | MUST HAVE | US-03 | Purnima | Done
Sprint 1 | Sprint 1 | US-05 | As a researcher, I want the requested number of personas to be generated consistently so that the research sample is predictable. | MUST HAVE | US-03 | Purnima | Done
Sprint 1 | Sprint 1 | US-06 | As a researcher, I want malformed or incomplete LLM responses to be normalized so that the application remains usable. | SHOULD HAVE | US-05 | Purnima | Done
Sprint 1 | Sprint 1 | US-07 | As a user, I want generated personas displayed as selectable cards so that I can quickly review and choose a persona. | MUST HAVE | US-04 | Purnima | Done
Sprint 2 | Sprint 2 | US-08 | As a researcher, I want to select a persona and start an AI interview so that I can simulate a customer conversation. | MUST HAVE | US-07 | Purnima | Done
Sprint 2 | Sprint 2 | US-09 | As a researcher, I want persona memory to retain important interview information so that the conversation remains consistent. | MUST HAVE | US-08 | Purnima | Done
Sprint 2 | Sprint 2 | US-10 | As a researcher, I want to ask the same survey question to multiple personas so that I can compare customer responses. | MUST HAVE | US-03 | Purnima | Done
Sprint 2 | Sprint 2 | US-11 | As a researcher, I want survey responses normalized into a consistent structure so that results can be displayed reliably. | SHOULD HAVE | US-10 | Purnima | Done
Sprint 2 | Sprint 2 | US-12 | As a researcher, I want persona-level research insights from an interview so that I can identify evidence-based findings. | MUST HAVE | US-09 | Purnima | Done
Sprint 2 | Sprint 2 | US-13 | As a researcher, I want the insight agent to avoid unsupported claims so that research findings remain grounded in interview evidence. | SHOULD HAVE | US-12 | Purnima | Done
Sprint 2 | Sprint 2 | US-14 | As a researcher, I want product adoption intent scored from the persona and interview so that I can estimate likelihood of product use. | SHOULD HAVE | US-09, US-12 | Purnima | Done
Sprint 3 | Sprint 3 | US-15 | As a researcher, I want cross-persona survey insights so that common patterns and differences are identified across the sample. | MUST HAVE | US-10, US-11 | Purnima | Done
Sprint 3 | Sprint 3 | US-16 | As a user, I want clear loading, success and error states so that I understand what the application is doing. | SHOULD HAVE | US-03, US-08, US-10 | Purnima | Done
Sprint 3 | Sprint 3 | US-17 | As a user, I want a responsive research workspace so that I can use persona, survey and insight features from one interface. | MUST HAVE | US-07, US-10, US-12 | Purnima | Done
Sprint 3 | Sprint 3 | US-18 | As a developer, I want health and API routes organized in FastAPI so that the backend can be tested and maintained. | MUST HAVE | US-02, US-08 | Purnima | Done
Sprint 3 | Sprint 3 | US-19 | As a developer, I want the frontend and backend connected through REST endpoints so that user actions trigger AI workflows correctly. | MUST HAVE | US-18 | Purnima | Done
Sprint 3 | Sprint 3 | US-20 | As a developer, I want project documentation and setup instructions so that the SUGP project can be installed and evaluated. | SHOULD HAVE | US-18, US-19 | Purnima | Done
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours. Day columns show remaining effort at the end of each day; each task counts down to 0.
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
TOTAL | [7 empty] | 188 | 133.9 | 79.3 | 36.5 | 6.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-01 | T-01 | Define startup idea, product description and target audience input fields | 2026-07-01 | 2026-07-02 | Chirag | Frontend / Design | Done | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T-02 | Implement validated research input schema in FastAPI | 2026-07-02 | 2026-07-03 | Chirag | Backend / Coding | Done | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-03 | Add input validation and safe error responses for incomplete requests | 2026-07-03 | 2026-07-04 | Chirag | Backend / Coding | Done | 5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-04 | Create Ollama persona-generation prompt and model configuration | 2026-07-04 | 2026-07-06 | Chirag | Prompt Engineering | Done | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-05 | Normalize persona fields and ensure required attributes are present | 2026-07-05 | 2026-07-07 | Chirag | AI / Validation | Done | 7 | 4.7 | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T-06 | Add retry and count validation for exact persona generation | 2026-07-06 | 2026-07-08 | Chirag | Backend / Testing | Done | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T-07 | Handle malformed JSON and inconsistent LLM outputs safely | 2026-07-08 | 2026-07-09 | Chirag | Backend / Testing | Done | 5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T-08 | Build persona cards and selection workflow in the frontend | 2026-07-09 | 2026-07-13 | Chirag | Frontend / Coding | Done | 10 | 7.5 | 5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-08 | T-09 | Connect selected persona to interview/chat endpoint | 2026-07-14 | 2026-07-16 | Chirag | Backend / Frontend | Done | 9 | 6.8 | 4.5 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T-10 | Implement persona conversation memory and important-point storage | 2026-07-16 | 2026-07-18 | Chirag | Backend / Coding | Done | 10 | 7.5 | 5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T-11 | Implement multi-persona survey request and response workflow | 2026-07-18 | 2026-07-21 | Chirag | AI / Backend | Done | 11 | 8.8 | 6.6 | 4.4 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T-12 | Normalize survey response objects and persona identifiers | 2026-07-21 | 2026-07-23 | Chirag | Backend / Testing | Done | 7 | 4.7 | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-12 | T-13 | Implement evidence-based persona research insight generation | 2026-07-22 | 2026-07-25 | Chirag | AI / Prompt Engineering | Done | 10 | 7.5 | 5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-13 | T-14 | Add safeguards against unsupported recommendations and claims | 2026-07-24 | 2026-07-26 | Chirag | AI / Validation | Done | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-14 | T-15 | Implement product adoption scoring from persona interview evidence | 2026-07-27 | 2026-07-29 | Chirag | AI / Backend | Done | 9 | 6.8 | 4.5 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
US-15 | T-16 | Implement cross-persona survey insight comparison | 2026-08-05 | 2026-08-07 | Chirag | AI / Analysis | Done | 10 | 7.5 | 5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-16 | T-17 | Add loading, success, empty and error states across workflows | 2026-08-06 | 2026-08-09 | Chirag | Frontend / Testing | Done | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-17 | T-18 | Integrate research workspace sections and responsive UI behaviour | 2026-08-08 | 2026-08-12 | Chirag | Frontend / Design | Done | 10 | 7.5 | 5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-18 | T-19 | Organize FastAPI routes including health and research endpoints | 2026-08-10 | 2026-08-13 | Chirag | Backend / Coding | Done | 7 | 4.7 | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-19 | T-20 | Test frontend REST calls for generation, chat, survey, insights and adoption | 2026-08-12 | 2026-08-16 | Chirag | Integration / Testing | Done | 11 | 8.8 | 6.6 | 4.4 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-20 | T-21 | Update README, project structure and local setup instructions | 2026-08-16 | 2026-08-18 | Chirag | Documentation | Done | 5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-20 | T-22 | Add MIT License and clean repository files for submission | 2026-08-18 | 2026-08-20 | Chirag | Documentation / Git | Done | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-19 | T-23 | Perform end-to-end regression testing and fix integration issues | 2026-08-20 | 2026-08-24 | Chirag | Testing / Debugging | Done | 12 | 9.6 | 7.2 | 4.8 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-20 | T-24 | Final submission review: backend, frontend, Agile document and GitHub readiness | 2026-08-25 | 2026-08-29 | Chirag | Final QA | Done | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | 2 | Initial LLM output occasionally returned incomplete JSON or fewer persona objects than requested. | Added JSON cleanup, required-field normalization and retry/count validation before accepting the response.
Sprint 1 | 5 | Frontend and backend payload fields needed to stay consistent when persona data changed. | Aligned request/response fields and tested the generation workflow end to end.
Sprint 1 | 9 | Persona cards became difficult to scan when many attributes were displayed together. | Grouped profile information into structured card sections and kept the selection action clear.
Sprint 2 | 3 | Interview responses could lose context between consecutive questions. | Connected persona-specific memory and stored conversation plus important research points.
Sprint 2 | 7 | Survey responses from different personas were not always returned in the same shape. | Added normalization and safe defaults before returning survey results to the frontend.
Sprint 2 | 11 | Insight generation could make claims that were not explicitly supported by the interview. | Strengthened the insight prompt and validation rules to use interview evidence only.
Sprint 3 | 2 | Cross-persona insight generation needed all responses to be compared rather than analyzing one persona. | Implemented aggregation across the full persona set and added structured comparison output.
Sprint 3 | 6 | Several frontend actions needed clear feedback while AI requests were running. | Added loading, empty, success and error states for major workflows.
Sprint 3 | 10 | Final project documentation did not exactly match the repository structure. | Updated README setup and structure details, then reviewed backend/frontend paths before submission.
Sprint 3 | 14 | Submission required an open-source license and clean repository contents. | Added MIT License, reviewed ignored files and completed final end-to-end checks.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-07-01 | 2026-07-13 | Chirag | Start breaking AI features into small testable tasks before coding. Define input/output contracts before connecting frontend and backend. Maintain a short daily implementation checklist. | Stop changing prompt structure and frontend payloads at the same time. Avoid keeping temporary test code in the main project files. | Continue validating LLM output instead of trusting raw model responses. Continue using Git commits after stable milestones and testing the complete generation flow. | Created a clearer generation contract, separated validation from UI work, cleaned temporary files, and committed the stable Ollama persona-generation milestone.
2 | Sprint 2 | 2026-07-14 | 2026-08-04 | Chirag | Start testing memory, survey and insight workflows with multiple personas early. Start recording edge cases for malformed AI responses and empty research states. | Stop testing only the happy path. Avoid assuming that every LLM response will have the expected JSON structure or every persona will answer every survey question. | Continue evidence-based prompting, normalization and incremental integration testing. Continue keeping backend responsibilities separated into generator, chat, memory, survey and insight modules. | Added persona memory handling, survey normalization, evidence-focused insight rules and adoption analysis; tested empty and inconsistent response cases.
3 | Sprint 3 | 2026-08-05 | 2026-08-29 | Chirag | Start doing a final repository/documentation audit before the last day of the sprint. Start checking frontend, backend, README, license and Agile evidence as one submission package. | Stop leaving documentation updates until the end. Avoid repository clutter such as generated cache files and outdated setup instructions. | Continue end-to-end testing and keeping UI states understandable. Continue making research outputs structured so that results are easy to interpret. | Completed cross-persona survey insights, frontend feedback states, integration/regression testing, README corrections, MIT License addition and final submission review.